## Overview
School-X Feature/User Story QA Tracker
Updated | 2026-06-24 15:40 KST
Canonical Workbook | docs/qa/schoolx-feature-user-story-tracker.xlsx
Source Scope | Routes, components, server services, domain types, mock data, migrations/docs overview, and existing tests.
Current Phase | Inventory complete; active defects fixed/retested; all executable tracked stories now have coverage evidence or explicit dormant N/A status.
Next Phase | Maintain dormant UI backlog intentionally and add live external-provider checks when Google/Supabase test fixtures are available.
Feature Rows | 72
Open Defects | 0
Dormant/Backlog Items | 5
Status | Count | Meaning | Action
Implemented | 69 | Code path is mounted or API is active. | Test according to story.
Implemented With UX Issue | 0 | Works but has a documented UX/logistical issue. | Fix then retest.
API Implemented; UI Dormant | 2 | Backend exists but no active mounted UI. | Test API and decide UI handling.
Dormant/Incomplete | 1 | Component exists but is not mounted or lacks handlers. | Do not treat as done behavior.
Planned | 0 | Tracked but not implemented. | Backlog only.
Priority | Count | Definition | Required Response
P0 | 0 | Security/data-loss/blocking production issue. | Stop and fix immediately.
P1 | 0 | Major workflow blocked or high-risk regression. | Fix before release.
P2 | 1 | Important UX/logistical issue with clear user impact. | Fix in this goal.
P3 | 5 | Moderate polish or confusing behavior. | Fix if low-risk in this goal.
P4 | 1 | Dormant cleanup or low-risk maintenance. | Track unless it blocks testing.

## Feature Stories
ID | Area | Feature | User Story | Actor | Entry Point | Expected Behavior | Code References | Implementation Status | Test Status | Existing Coverage | Manual Test Script | Defects | Fix Status | Retest Status
F001 | Auth | Root auth redirect | As a visitor, I want the app root to send me to the right place so I do not land on a blank shell. | Visitor or signed-in user | / | Unauthenticated users redirect to /login; authenticated users redirect to /office. | src/app/page.tsx; src/server/auth/get-current-user.ts | Implemented | E2E Smoke Covered | tests/e2e/smoke.spec.ts | Visit / while unauthenticated and authenticated; confirm redirects. |  | No Defect | Passed
F002 | Auth | Login page and error messaging | As an approved teacher, I want a clear login page with actionable errors so I know how to enter the office. | Approved or unapproved teacher | /login | Shows Google login, optional dev admin login by host/env, mock-mode hint, and not-approved/oauth/dev-login error messages. | src/app/(auth)/login/page.tsx; src/server/auth/dev-login.ts | Implemented | E2E Smoke Covered | tests/e2e/smoke.spec.ts | Open /login and verify heading, Google CTA, conditional dev CTA, and each error query string. |  | No Defect | Passed
F003 | Auth | Google OAuth start and approved-user onboarding | As an approved Google user, I want OAuth to create or refresh my profile and room access so I can use the office. | Approved Google user | /auth/login; /auth/callback | OAuth redirects to Google, exchanges callback code, rejects inactive or missing allowed users, creates/updates profile, grants all rooms for admins or configured all-room users, otherwise grants meeting membership. | src/app/auth/login/route.ts; src/app/auth/callback/route.ts | Implemented | Unit Covered | tests/unit/auth-routes.test.ts | Exercise OAuth callback with approved, inactive, and missing allowed-user cases in integration or route tests. |  | No Defect | Passed
F004 | Auth | Development login | As a local developer, I want a safe dev login path so I can test admin-only flows without OAuth. | Developer | /auth/dev-login | When enabled for the host, the route verifies an active allowed user/profile, clears stale Supabase cookies, sets the app session cookie, and redirects only to safe relative next paths. | src/app/auth/dev-login/route.ts; src/server/auth/dev-login.ts | Implemented | Unit Covered | tests/unit/auth-routes.test.ts | Call /auth/dev-login with enabled/disabled env and safe/unsafe next values. |  | No Defect | Passed
F005 | Auth | Logout | As a signed-in user, I want logout to reliably clear session state so another user cannot inherit my session. | Signed-in user | /logout; header logout button | Prefetch requests return 204; real logout signs out Supabase when active, clears Supabase and app-session cookies, and redirects to /login. | src/app/logout/route.ts; src/components/layout/TopHeader.tsx | Implemented | Unit Covered | tests/unit/auth-routes.test.ts | Click logout and verify cookies are cleared and /login loads; verify prefetch returns 204. |  | No Defect | Passed
F006 | Auth/Ops | Auth diagnostics | As an operator, I want gated auth diagnostics so I can debug cookie/session state without exposing it in production. | Operator | /auth/status; /api/auth/debug | Diagnostics are available only when auth debug is enabled; response reports current project cookies, Supabase/app-session state, and mock/supabase mode. | src/app/auth/status/page.tsx; src/app/api/auth/debug/route.ts; src/lib/env.ts | Implemented | Unit Covered | tests/unit/env-guards.test.ts | Verify 404 when disabled; verify safe diagnostic fields when enabled. |  | No Defect | Passed
F007 | Shell/Profile | Top header and profile settings | As a signed-in user, I want to see my identity, update my profile, reach admin when allowed, and sign out. | Signed-in user | Top header | Header links to /office, shows auth/admin status, opens profile dialog, saves display name/avatar/bio with validation and audit log, shows admin settings only for admins, and exposes logout. | src/components/layout/TopHeader.tsx; src/components/layout/ProfileSettingsDialog.tsx; src/app/api/profile/route.ts | Implemented | Component Covered | tests/components/top-header.test.tsx | Open profile dialog; save valid/invalid fields; verify admin link visibility. |  | No Defect | Passed
F008 | Navigation | Sidebar room navigation | As a room member, I want navigation to show which rooms I can enter so I do not click locked rooms. | Room member | App shell sidebar | Meeting is listed first; department and project rooms follow; rooms without membership render disabled with lock icon; accessible rooms link to /rooms/{id}. | src/components/layout/SidebarPanel.tsx; src/components/layout/AppShell.tsx | Implemented | Component + Browser Covered | tests/components/sidebar-panel.test.tsx; post-fix browser retest | Open a room page with mixed memberships; verify accessible links and locked rows. | D002 | Fixed | Passed
F009 | Config/Ops | Environment mode guards and health check | As an operator, I want safe mock/supabase mode selection and a minimal health endpoint so deploys fail safely. | Operator | /api/health; env loading | Development can use mock fallback; production rejects mock mode or missing Supabase service role; health returns ok/degraded without secrets. | src/lib/env.ts; src/app/api/health/route.ts; src/instrumentation.ts | Implemented | Unit Covered | tests/unit/env-guards.test.ts | Run health in mock and supabase-configured modes; verify production guard behavior. |  | No Defect | Passed
F010 | Office | Office floor plan | As a member, I want a visual office map so I can enter active rooms and understand room purpose. | Room member | /office | Shows active room layout for finance, planning, external, meeting, development, research, promotion, province research, Gwangju-Hanam research, and science museum; inactive city room is omitted from map; membership controls open/locked state; each active non-meeting room shows resident bot. | src/components/office/OfficeFloorPlan.tsx; src/components/office/RoomCard.tsx; src/lib/mock-data.ts | Implemented | Covered | tests/components/cards.test.tsx; tests/e2e/smoke.spec.ts | Open /office and verify active rooms, bot labels, locked state, and links. |  | No Defect | Passed
F011 | Office/Ops | Operation status card | As an operator, I want today's shared items, briefings, and active tasks at a glance so I can triage work. | Room member | /office side panel | Initial server snapshot renders, then client refreshes /api/office/operation-status every 15 seconds; stale/error state changes pill to confirmation-needed. | src/components/office/OperationStatusCard.tsx; src/app/api/office/operation-status/route.ts; src/server/office/operation-status-service.ts | Implemented | Unit Covered | tests/unit/operation-status.test.ts | Open office and stub status API success/failure; verify counts and status pill. |  | No Defect | Passed
F012 | Office | Meeting side panel quick actions and recent shares | As a member, I want meeting-room shortcuts and recent shared cards so I can quickly move work into the hub. | Room member | /office side panel | Shows meeting hub copy, four shortcuts that navigate to /rooms/meeting, compact video meeting panel, up to three recent meeting shared items, and a data-flow note. | src/components/office/MeetingSidePanel.tsx | Implemented | Component + E2E Smoke Covered | tests/components/cards.test.tsx; tests/e2e/smoke.spec.ts | Open /office and click each shortcut; verify recent shared card presence/empty state. |  | No Defect | Passed
F013 | Rooms | Room workspace shell | As a room member, I want a clear room header and panels so I understand where I am and who/what is active. | Room member | /rooms/{roomId} | Header shows back button, room icon/name/type, resident-bot status or no-bot status, member avatar stack, active meeting banner for meeting room, chat, description, video panel for meeting, and right panel. | src/components/rooms/RoomWorkspace.tsx; src/server/rooms/get-room-view.ts | Implemented | E2E Smoke Covered | tests/e2e/smoke.spec.ts | Open meeting and a work room; verify header, panels, and meeting-only sections. |  | No Defect | Passed
F014 | Rooms/Auth | Room access and active-room gating | As a user, I should only enter active rooms where I have membership. | Room member | /rooms/{roomId} | Room page requires auth; missing membership returns forbidden via server guard; inactive or unknown room returns notFound; active rooms load view model. | src/app/(workspace)/rooms/[roomId]/page.tsx; src/server/rooms/get-room-view.ts; src/server/auth/require-room-member.ts | Implemented | Unit + E2E Smoke Covered | tests/unit/room-decision-task.test.ts; tests/unit/list-route-authorization.test.ts; tests/e2e/smoke.spec.ts | Attempt accessible, inaccessible, inactive city_research, and missing room routes. |  | No Defect | Passed for inactive room and accessible mock routes
F015 | Threads | Thread selection | As a room member, I want to switch between conversations so each topic has its own context. | Room member | Room chat header | Thread select pushes ?threadId=... and resolveRoomThread verifies the selected thread belongs to the current room before loading messages. | src/components/rooms/RoomThreadControls.tsx; src/server/rooms/thread-service.ts | Implemented | Unit Covered | tests/unit/thread-context.test.ts | Create or seed multiple threads, switch select, and verify messages change. |  | No Defect | Passed
F016 | Threads | New thread with carryover summary | As a room member, I want a fresh conversation to inherit only useful summaries so the bot has continuity without replaying old chats. | Room member | New conversation button | POST creates an active thread with title or auto title, builds carryover summary from room memory, previous thread summary, recent decisions, and active tasks, and writes audit log. | src/components/rooms/RoomThreadControls.tsx; src/server/rooms/thread-service.ts; src/app/api/rooms/[roomId]/threads/route.ts | Implemented | Unit Covered | tests/unit/thread-context.test.ts | Click 새 대화, verify new query thread and carryover summary via API/store. |  | No Defect | Passed
F017 | Threads | Rename thread | As a room member, I want to rename a conversation so I can identify it later. | Room member | Thread title edit button | Edit mode preloads active title; empty title shows inline error; PATCH trims/saves title, updates override, refreshes, and audits. | src/components/rooms/RoomThreadControls.tsx; src/app/api/rooms/[roomId]/threads/[threadId]/route.ts | Implemented | Component Covered | tests/components/room-interactions.test.tsx | Edit title to empty and valid values; verify select label and API payload. |  | No Defect | Passed
F018 | Chat | Message timeline scrolling | As a reader, I want new messages to appear without losing my place when I am reviewing older messages. | Room member | Message timeline | Timeline autoscrolls only when near bottom; when scrolled up, new messages trigger a floating 새 메시지 button that scrolls to bottom. | src/components/rooms/MessageTimeline.tsx | Implemented | Component Covered | tests/components/room-interactions.test.tsx | Populate many messages, scroll up, trigger new message, verify button and scroll behavior. |  | No Defect | Passed
F019 | Chat | Human message send | As a room member, I want to send messages quickly and recover from errors. | Room member | Message composer | Enter submits, Shift+Enter adds newline, empty text and in-flight submits are disabled, an optimistic message is shown, committed server message replaces it, and failures remove optimistic state with error alert. | src/components/rooms/MessageComposer.tsx; src/app/api/rooms/[roomId]/messages/route.ts; src/server/messages/room-message-service.ts | Implemented | Browser Covered | post-fix browser retest; API service covered by related message/thread tests | Send valid, empty, newline, and failing messages; verify UI state and API. |  | No Defect | Passed
F020 | Chat | Message polling and merge | As a room member, I want other people's and bot messages to appear without refreshing. | Room member | Room chat | Client polls current thread every 4 seconds when visible; no-store GET returns thread messages; merge keeps optimistic and pending messages while applying server updates. | src/components/rooms/RoomChat.tsx; src/lib/merge-messages.ts | Implemented | Unit Covered | tests/unit/merge-messages.test.ts | Stub polling response with new and duplicate messages; verify no duplicate or lost optimistic entries. |  | No Defect | Passed
F021 | Chat/Bots | Room resident bot toggle | As a work-room member, I want to decide whether the resident bot should respond to my message. | Room member | Work-room composer | Resident bot toggle is enabled by default in non-meeting rooms with an agent; disabling sends only human message; enabling starts a room agent run after the message is committed. | src/components/rooms/MessageComposer.tsx; src/server/agents/run-agent.ts | Implemented | Component + Unit Covered | tests/components/room-interactions.test.tsx; tests/unit/development-agent.test.ts | In a work room, send with toggle on/off; verify agent-runs payloads. |  | No Defect | Passed
F022 | Chat/Bots | Development bot guest in work rooms | As a work-room member, I want to call the development bot as an extra guest so platform improvement ideas are captured. | Room member | Work-room composer | Non-meeting rooms include development bot as guest when it is not the resident agent; selecting it calls POST /agent-runs with mode room and development_request intent. | src/server/rooms/get-room-view.ts; src/components/rooms/MessageComposer.tsx; src/lib/agents/development-agent.ts | Implemented | Unit Covered | tests/unit/development-agent.test.ts | Open non-development room, select development bot, send message, verify run payload and label. |  | No Defect | Passed
F023 | Chat/Bots | Meeting-room guest bot calls | As a meeting participant, I want to call domain bots into the meeting room for short briefings. | Meeting participant | Meeting-room composer | Meeting composer shows coordinator bot plus writable-room bots and development bot; selected guests run with mode meeting_guest, guestSourceRoomId, and development_request intent for development bot. | src/server/rooms/get-room-view.ts; src/components/rooms/MessageComposer.tsx | Implemented | Unit Covered | tests/unit/development-agent.test.ts; tests/unit/coordinator-briefing.test.ts | Select one or more meeting guest bots, send message, verify pending messages and payloads. |  | No Defect | Passed
F024 | Chat/Bots | Agent-run pending, completion, failure, and cancellation | As a user who calls a bot, I want visible progress and the ability to stop a long run. | Room member | Pending bot message | Queued run creates pending message with activity; client polls run detail up to 60 attempts; output replaces pending message; failed/cancelled runs become system messages; cancel button sends DELETE and shows retryable error on failure. | src/components/rooms/RoomChat.tsx; src/components/rooms/MessageBubble.tsx; src/app/api/rooms/[roomId]/agent-runs/[runId]/route.ts; src/server/agents/run-agent.ts | Implemented | Unit Covered | tests/unit/agent-run-detail.test.ts; tests/unit/agent-run-concurrency.test.ts | Stub run states queued/running/completed/failed/cancelled and cancel failure/success. |  | No Defect | Passed
F025 | Chat | Message rendering and copy | As a reader, I want messages to clearly show speaker, time, type, and copy controls. | Room member | Message timeline | Own, other human, agent, guest-agent, system, video-meeting, shared-item, and meeting-import messages render with appropriate visual treatment; copy buttons are present. | src/components/rooms/MessageBubble.tsx; src/components/rooms/MessageCopyButton.tsx | Implemented | Component Covered | tests/components/message-bubble.test.tsx | Render all message types; verify sender labels, copy behavior, and shared/import embedded cards. |  | No Defect | Passed
F026 | Chat/Files | Generated files in agent messages | As a user, I want files generated by a bot to be downloadable from the message that produced them. | Room member | Agent message bubble | Metadata generatedFiles renders file name, size, and download button; download uses signed URL route scoped to the message room. | src/components/rooms/MessageBubble.tsx; src/components/files/FileDownloadButton.tsx; src/server/files/file-service.ts | Implemented | Component Covered | tests/components/message-bubble.test.tsx | Seed an agent message with generatedFiles metadata and verify download route call. |  | No Defect | Passed
F027 | Agents | Agent persona editor visibility | As a room admin, I want to expand and edit the bot persona; as a non-admin, I should see it read-only. | Room admin or member | Room right panel | Agent rooms show a collapsed persona editor; canEdit is true only for admin membership; text areas and save/publish are disabled for non-admins. | src/components/agents/AgentPersonaEditor.tsx; src/components/rooms/RoomRightPanel.tsx | Implemented | Unit Covered | tests/unit/agent-persona-service.test.ts | Open as admin and member; verify disabled states and expand/collapse. |  | No Defect | Passed
F028 | Agents | Save persona draft | As a room admin, I want to save persona drafts without publishing to the live agent. | Room admin | Persona editor | PATCH validates/normalizes persona fields with max lengths, saves draft, updates draft timestamp, refreshes, and shows success or error. | src/components/agents/AgentPersonaEditor.tsx; src/app/api/rooms/[roomId]/agent-persona/route.ts; src/server/agents/agent-persona-service.ts | Implemented | Unit Covered | tests/unit/agent-persona-service.test.ts | Save normal, empty, and overlong fields; verify normalization and notice. |  | No Defect | Passed
F029 | Agents | Publish persona | As a room admin, I want published persona changes to update the app and Claude Managed Agent when configured. | Room admin | Persona editor | POST publishes draft/local persona, attempts Anthropic update when configured, stores published timestamp/version, and reports local-only or Anthropic-updated status. | src/components/agents/AgentPersonaEditor.tsx; src/app/api/rooms/[roomId]/agent-persona/publish/route.ts; src/server/agents/agent-persona-service.ts | Implemented | Unit Covered | tests/unit/agent-persona-service.test.ts | Publish with real agents disabled and enabled-missing config; verify notice and stored state. |  | No Defect | Passed
F030 | Agents/Ops | Agent-run concurrency and stuck-run sweep | As an operator, I want bot runs constrained and stale runs cleaned up so one room cannot pile up infinite work. | Operator | Agent run service; /api/agent-runs/sweep | StartAgentRun enforces active run limits; cron sweep requires Bearer CRON_SECRET and cancels stuck queued/running/idle/requires_action runs. | src/server/agents/run-agent.ts; src/app/api/agent-runs/sweep/route.ts | Implemented | Unit Covered | tests/unit/agent-run-concurrency.test.ts; tests/unit/agent-run-sweep.test.ts | Run route with missing, wrong, and correct CRON_SECRET; verify sweep result. |  | No Defect | Passed
F031 | Files | File list and upload | As a room member, I want to upload and see room files so work artifacts stay with the room. | Room member | Room right panel file card | File list shows count, file name, version, size, access level, empty state, upload button, and upload result message; POST uses multipart file and roomId. | src/components/files/FileList.tsx; src/components/files/FileUploadForm.tsx; src/app/api/files/route.ts; src/server/files/file-service.ts | Implemented | Unit Covered | tests/unit/file-upload-limits.test.ts | Upload allowed and disallowed files; verify list refresh and error messages. |  | No Defect | Passed
F032 | Files | Signed file download | As a room member, I want to download files I can access without exposing storage internals. | Room member | File download button | Download route verifies user/room access and returns signed URL plus file metadata; client creates a temporary anchor and shows inline error on failure. | src/components/files/FileDownloadButton.tsx; src/app/api/files/[id]/download/route.ts; src/server/files/file-service.ts | Implemented | Unit + Component Covered | tests/unit/file-upload-limits.test.ts; tests/components/message-bubble.test.tsx | Click download for accessible and inaccessible files; verify signedUrl handling. |  | No Defect | Passed
F033 | Files | Delete room file access | As a room member, I want to remove a file from the current room without breaking other rooms' shared access. | Room member | File delete button | Confirmation dialog calls DELETE /api/files; service removes this room's access and keeps other shared room access; UI refreshes and shows errors. | src/components/files/FileDeleteButton.tsx; src/app/api/files/route.ts; src/server/files/file-service.ts | Implemented | Unit Covered | tests/unit/share-import-service.test.ts | Delete a file shared to another room; verify current room access removed and target room access remains. |  | No Defect | Passed
F034 | Files/API | Create file version | As an integration or agent, I want to record a new version so file history is preserved. | Integration or agent | POST /api/files/{id}/versions | Route validates roomId/changeSummary and creates a new version for an accessible room file. | src/app/api/files/[id]/versions/route.ts; src/server/files/file-service.ts | Implemented | Unit Covered | tests/unit/file-upload-limits.test.ts | Call version route for accessible/inaccessible file and verify versionNo/history. |  | No Defect | Passed
F035 | Files/Sharing | File share target discovery | As a room member, I want only writable target rooms to appear when sharing files. | Room member | Share selected files dialog | GET /api/files/share-targets excludes source room and requires canWriteRoom for targets; dialog lazily loads targets and shows empty/error states. | src/components/files/FileList.tsx; src/app/api/files/share-targets/route.ts; src/server/collaboration/share-import-service.ts | Implemented | Component Covered | tests/components/cards.test.tsx | Open dialog with mixed memberships; verify target list. |  | No Defect | Passed
F036 | Files/Sharing | Bulk share selected files to rooms | As a room member, I want to share selected files to other rooms with a visible card in each target. | Room member | Share selected files dialog | Selected files and target rooms are required; POST creates shared_items, grants target file access, posts corresponding shared/import context where applicable, audits, clears selection, refreshes, and closes dialog. | src/components/files/FileList.tsx; src/app/api/files/share/route.ts; src/server/collaboration/share-import-service.ts | Implemented | Component/Unit Covered | tests/components/cards.test.tsx; tests/unit/share-import-service.test.ts | Select one file and one target; verify shared item, target file access, and UI refresh. |  | No Defect | Passed
F037 | Sharing | Visible shared-items list isolation | As a user, I should only see shared items from rooms I am allowed to access. | Room member | Room right panel; /api/shared-items | List route and service filter shared items by membership and optional roomId; missing membership returns forbidden. | src/app/api/shared-items/route.ts; src/server/collaboration/share-import-service.ts | Implemented | Unit Covered | tests/unit/list-route-authorization.test.ts | Query with no room and specific accessible/inaccessible room. |  | No Defect | Passed
F038 | Sharing | Open shared original locally | As a user reviewing a shared file, I want to download and open the original file in a chosen local folder. | Room member | Shared item card | Dialog accepts download directory, POST downloads accessible source file to local folder and opens it with default app; result path or error is shown. | src/components/meeting/SharedItemCard.tsx; src/app/api/shared-items/[id]/open-original/route.ts; src/server/collaboration/share-import-service.ts | Implemented | Component Covered | tests/components/cards.test.tsx | Open original for file-backed and non-file shared items; verify disabled state and result path. |  | No Defect | Passed
F039 | Sharing | Delete shared item | As a room member, I want to remove a shared card without deleting the original file. | Room member | Shared item card | Confirmation DELETE removes shared item visibility and leaves source file intact; error is shown on failure. | src/components/meeting/SharedItemCard.tsx; src/app/api/shared-items/[id]/route.ts; src/server/collaboration/share-import-service.ts | Implemented | Component Covered | tests/components/cards.test.tsx | Delete shared item and verify original file remains. |  | No Defect | Passed
F040 | Sharing/Imports | Import meeting shared item to work rooms | As a meeting participant, I want to bring a meeting shared item into selected work rooms. | Meeting participant | Shared item card in meeting room | Only meeting-target shared items show import button; dialog loads writable non-meeting targets; POST creates meeting_imports and file copies/access for selected rooms; notice/error shown. | src/components/meeting/SharedItemCard.tsx; src/app/api/meeting-imports/route.ts; src/app/api/meeting-imports/targets/route.ts; src/server/collaboration/share-import-service.ts | Implemented | Unit + Component Covered | tests/unit/share-import-service.test.ts; tests/components/cards.test.tsx | Import to one and multiple rooms; verify copied access and room right panel import. | D004 | Fixed | Passed
F041 | Imports | Apply meeting import to bot memory | As a work-room member, I want imported meeting context to be applied to the room bot memory queue. | Room member | Meeting import card | Pending import can POST apply; service verifies access, appends pending context, marks import processed, shows notice, disables both actions, and refreshes. | src/components/meeting/MeetingImportCard.tsx; src/app/api/meeting-imports/[id]/apply/route.ts; src/server/collaboration/share-import-service.ts | Implemented | Unit Covered | tests/unit/share-import-service.test.ts | Apply pending import; verify memory pending context and processed status. |  | No Defect | Passed
F042 | Imports/Tasks | Create task from meeting import | As a work-room member, I want an import to become a task when it needs follow-up. | Room member | Meeting import card | Pending import can POST task; service creates task, marks import processed, shows notice, disables actions, and refreshes. | src/components/meeting/MeetingImportCard.tsx; src/app/api/meeting-imports/[id]/task/route.ts; src/server/collaboration/share-import-service.ts | Implemented | Unit Covered | tests/unit/share-import-service.test.ts | Create task from import; verify task visible in meeting and target room. |  | No Defect | Passed
F043 | Imports | Delete meeting import | As a work-room member, I want to dismiss/remove an import record without deleting copied files. | Room member | Meeting import card | Confirmation DELETE removes import record while file copies remain managed separately; UI refreshes or shows error. | src/components/meeting/MeetingImportCard.tsx; src/app/api/meeting-imports/[id]/route.ts; src/server/collaboration/share-import-service.ts | Implemented | Component Covered | tests/components/cards.test.tsx | Delete import and verify copied file access still exists. |  | No Defect | Passed
F044 | Sharing/API | Share message/file to meeting API | As an integration or future UI, I want to create a shared item in the meeting room from a source message or file. | Integration or future UI | POST /api/shared-items | Route creates meeting-target shared item from sourceRoomId/sourceMessageId/sourceFileId/title/summary with access checks and default values. | src/app/api/shared-items/route.ts; src/server/collaboration/share-import-service.ts | API Implemented; UI Dormant | Unit Covered | tests/unit/share-import-service.test.ts | Call API for message-backed and file-backed shares; confirm FileShareToMeetingButton is not mounted. | D005 | Fixed | Passed - obsolete dormant button removed
F045 | Decisions | Meeting-scoped decisions list | As a room member, I want meeting decisions visible across rooms so everyone sees the same confirmed decisions. | Room member | Decision panel | GET and room view always read decisions from meeting scope; all room panels display the list; non-meeting rooms do not show edit controls. | src/components/rooms/DecisionTaskPanel.tsx; src/app/api/decisions/route.ts; src/server/rooms/get-room-view.ts | Implemented | Unit Covered | tests/unit/room-decision-task.test.ts | Create meeting decision and verify it appears in multiple rooms. |  | No Defect | Passed
F046 | Decisions | Create meeting decision | As a meeting-room writer, I want to add decisions so they become shared reference points. | Meeting room writer | Decision panel in meeting room | Create button appears only in meeting room; title is required; POST requires meeting membership and writable role; creates decision and audit log. | src/components/rooms/DecisionTaskPanel.tsx; src/app/api/decisions/route.ts | Implemented | Unit Covered | tests/unit/room-decision-task.test.ts | Create with empty and valid title as writer/observer. |  | No Defect | Passed
F047 | Decisions | Edit and delete meeting decision | As a meeting-room writer, I want to correct or remove decisions when they change. | Meeting room writer | Decision panel in meeting room | Edit and delete controls appear only in meeting room; PATCH requires non-empty title and writable meeting role; DELETE removes decision; both audit. | src/components/rooms/DecisionTaskPanel.tsx; src/app/api/decisions/[id]/route.ts | Implemented | Unit Covered | tests/unit/room-decision-task.test.ts | Edit/delete as writer and observer; verify errors and audit. |  | No Defect | Passed
F048 | Tasks | Task list visibility | As a room member, I want tasks relevant to my room to be visible without leaking other rooms' tasks. | Room member | Task panel; /api/tasks | Room task list reads room-specific tasks; no-room API filters to tasks in member rooms or assigned to member rooms. | src/components/rooms/DecisionTaskPanel.tsx; src/app/api/tasks/route.ts | Implemented | Unit Covered | tests/unit/room-decision-task.test.ts | Seed tasks for accessible/inaccessible rooms and query both modes. |  | No Defect | Passed
F049 | Tasks | Create work-room task | As a work-room writer, I want to create a task that is visible in the work room and meeting room. | Work-room writer | Task panel in work room | Dialog defaults to current room; POST requires writable current room and meeting membership; creates meeting-scoped task assigned to current room; audits. | src/components/rooms/DecisionTaskPanel.tsx; src/app/api/tasks/route.ts | Implemented | Unit + Browser Covered | tests/unit/room-decision-task.test.ts; post-fix browser retest | Create from work room; verify task target pill and meeting visibility. | D003 | Fixed | Passed
F050 | Tasks | Create meeting task for selected work rooms | As a meeting-room writer, I want to create one task for each selected work room. | Meeting room writer | Task panel in meeting room | Meeting task dialog requires at least one non-meeting target; each target must be writable; creates meeting-scoped tasks assigned to target rooms and audits. | src/components/rooms/DecisionTaskPanel.tsx; src/app/api/tasks/route.ts | Implemented | Unit + Browser Covered | tests/unit/room-decision-task.test.ts; post-fix browser retest | Create from meeting with none, one, and multiple targets; verify project-room labels. | D003 | Fixed | Passed
F051 | Video Meetings | Active meeting panel refresh and reuse | As a member, I want one active meeting per room so everyone joins the same call. | Room member | Video meeting panel | Panel initializes from server state, polls active meeting every 15 seconds, shows current meeting when active, and start attempts reuse an existing active meeting. | src/components/video-meetings/VideoMeetingPanel.tsx; src/lib/video-meetings/service.ts | Implemented | Unit Covered | tests/unit/video-meeting-service.test.ts | Start meeting twice; verify one live meeting and panel updates. |  | No Defect | Passed
F052 | Video Meetings | Start Google Meet with consent | As a meeting-room member, I want to start a call and record consent settings before sensitive meeting features are used. | Meeting room writer | Video meeting start dialog | Dialog captures title, description, provider, recording/transcript/AI summary consent; POST creates or reuses live meeting; opens Meet URL; redirects to meeting room; manual link registration alert appears when needed. | src/components/video-meetings/VideoMeetingStartDialog.tsx; src/app/api/video-meetings/route.ts; src/lib/video-meetings/service.ts | Implemented | Unit/Component + Browser Covered | tests/unit/video-meeting-service.test.ts; tests/components/video-meeting.test.tsx; post-fix browser retest | Start with default and custom title; verify consent payload and stale default title. | D001 | Fixed | Passed
F053 | Video Meetings | Manual Google Meet join URL registration | As a meeting host, I want to register the generated Meet URL so everyone joins the same meeting. | Meeting host | Join URL form | When a meeting lacks registered URL, form opens Google Meet create URL, accepts a URL, PATCH normalizes/validates Meet URL, updates panel or reloads, and shows message/errors. | src/components/video-meetings/VideoMeetingJoinUrlForm.tsx; src/app/api/video-meetings/[id]/join-url/route.ts; src/lib/video-meetings/join-url.ts | Implemented | Unit Covered | tests/unit/video-meeting.test.ts; tests/unit/video-meeting-service.test.ts | Register valid and invalid Meet URLs; verify normalization and UI replacement with join button. |  | No Defect | Passed
F054 | Video Meetings | Join meeting | As a participant, I want to open the registered meeting URL with my School-X account hint and have my join intent recorded. | Meeting participant | Join meeting button/banner | Click validates URL presence, opens URL in new tab with authuser for Google Meet, POSTs join event, and shows error if logging fails. | src/components/video-meetings/VideoMeetingJoinButton.tsx; src/app/api/video-meetings/[id]/join/route.ts; src/lib/video-meetings/join-url.ts | Implemented | Component/Unit Covered | tests/components/video-meeting.test.tsx; tests/unit/video-meeting-service.test.ts | Click with registered and missing URL; verify window.open and event log. |  | No Defect | Passed
F055 | Video Meetings | End meeting | As a meeting-room member, I want to end the active meeting so the UI no longer routes users into stale calls. | Meeting participant | End meeting button/banner | POST ends meeting if user can end it; UI clears current meeting via callback or reloads; error is shown on failure. | src/components/video-meetings/VideoMeetingEndButton.tsx; src/app/api/video-meetings/[id]/end/route.ts; src/lib/video-meetings/service.ts | Implemented | Unit Covered | tests/unit/video-meeting-service.test.ts | End active, ended, and inaccessible meetings; verify panel changes. |  | No Defect | Passed
F056 | Video Meetings/Google | Automatic Google Meet link creation | As an operator, I want connected Google credentials to auto-register a Meet URL so hosts do not paste links manually. | Operator/meeting host | Meeting start service; Google connect | When Google credentials/token are configured, service creates Meet Space or Calendar event, stores normalized URL and provider metadata, and records events; failures fall back to manual registration. | src/lib/video-meetings/providers/google-meet.ts; src/server/integrations/google-oauth.ts; src/app/api/integrations/google/connect/route.ts; src/app/api/integrations/google/callback/route.ts | Implemented | Unit Covered | tests/unit/video-meeting-service.test.ts; tests/unit/token-crypto.test.ts | Connect Google token, start meeting, verify auto URL; simulate Meet API failure and Calendar fallback. |  | No Defect | Passed
F057 | Video Meetings/Zoom | Zoom provider and participant signature | As a member, I want Zoom available only when explicitly enabled and only with participant-level SDK signatures. | Room member | Provider picker; /api/video-meetings/zoom/signature | Zoom option is hidden unless NEXT_PUBLIC_ENABLE_ZOOM_EMBED=true; signature route requires auth, SDK env, registered active/scheduled meeting, and always uses participant role=0. | src/components/video-meetings/VideoMeetingProviderPicker.tsx; src/app/api/video-meetings/zoom/signature/route.ts; src/lib/video-meetings/permissions.ts | Implemented | Unit Covered | tests/unit/zoom-meeting-access.test.ts | Enable flag, create Zoom meeting, request signature for valid/invalid meeting numbers. |  | No Defect | Passed
F058 | Video Meetings/API | Meeting artifacts | As an integration, I want to attach transcripts, minutes, recordings, summaries, or provider metadata to a meeting. | Integration or operator | POST /api/video-meetings/{id}/artifacts | Route validates artifact type/title/content/http URL, verifies meeting access, creates artifact, and returns it. | src/app/api/video-meetings/[id]/artifacts/route.ts; src/lib/video-meetings/service.ts; src/components/video-meetings/VideoMeetingArtifactCard.tsx | API Implemented; UI Dormant | Unit + Component Covered | tests/unit/video-meeting-service.test.ts; tests/components/video-meeting.test.tsx | Call artifacts API with each artifact type and invalid externalUrl; inspect dormant card actions. | D006 | Fixed | Passed
F059 | Video Meetings/API | Meeting summary generation | As an operator, I want to generate an AI summary artifact from meeting data when consent allows. | Operator or integration | POST /api/video-meetings/{id}/summarize | Route calls summarizeVideoMeeting for an accessible meeting and returns the generated artifact; service enforces meeting access and summary behavior. | src/app/api/video-meetings/[id]/summarize/route.ts; src/lib/video-meetings/service.ts | Implemented | Unit Covered | tests/unit/video-meeting-service.test.ts | Call summarize for accessible/inaccessible meetings and with consent settings. |  | No Defect | Passed
F060 | Video Meetings/UI | Active meeting banner | As a meeting-room participant, I want active meetings visible at the top of chat. | Meeting participant | Meeting room workspace | Meeting room renders banner only when activeMeeting exists; banner shows provider, title, live status, join/end controls, and join URL registration form when missing. | src/components/video-meetings/ActiveVideoMeetingBanner.tsx; src/components/rooms/RoomWorkspace.tsx | Implemented | Component Covered | tests/components/video-meeting.test.tsx | Open meeting room with active meeting with and without URL. |  | No Defect | Passed
F061 | Video Meetings/UI | Meeting summary/artifact action stubs | As a meeting participant, I would expect summary/artifact action buttons to perform the named conversions. | Meeting participant | Dormant components | MeetingSummaryReview, CreateDecisionTaskFromSummary, VideoMeetingArtifactCard, ZoomMeetingEmbed, and ZoomFallbackCard exist but are not mounted in scanned routes; artifact action buttons have no handlers. | src/components/video-meetings/MeetingSummaryReview.tsx; src/components/video-meetings/CreateDecisionTaskFromSummary.tsx; src/components/video-meetings/VideoMeetingArtifactCard.tsx; src/components/video-meetings/ZoomMeetingEmbed.tsx; src/components/video-meetings/ZoomFallbackCard.tsx | Dormant/Incomplete | Component Covered | tests/components/video-meeting.test.tsx | Verify components are unmounted; if mounted later, add handlers or disable as unavailable. | D006 | Fixed | Passed - dormant actions disabled
F062 | Admin | Admin page access gate | As an admin, I want admin pages protected so non-admins cannot manage users. | Admin or non-admin | /admin; /admin/ops | Pages require admin; unauthenticated users redirect to login with next path; forbidden users redirect to /office. | src/app/(workspace)/admin/page.tsx; src/app/(workspace)/admin/ops/page.tsx; src/server/auth/require-user.ts | Implemented | E2E Smoke Covered | tests/e2e/smoke.spec.ts; post-fix browser retest for admin sidebar shell | Visit admin pages as admin, member, and unauthenticated user. |  | No Defect | Passed
F063 | Admin | Invite approved user | As an admin, I want to approve/invite an email and optionally mark it admin. | Admin | Admin dashboard invite form | Form requires email, accepts notes and admin checkbox; POST upserts allowed user in Supabase, grants all rooms when admin, logs audit; mock mode records audit only. | src/components/admin/AllowedUserForm.tsx; src/app/api/admin/allowed-users/route.ts | Implemented | Component Covered | tests/components/admin-controls.test.tsx | Invite valid/invalid email in mock and supabase mode; verify audit and admin grant. |  | No Defect | Passed
F064 | Admin | Allowed user active/admin toggles | As an admin, I want to activate/deactivate users and grant/revoke admin rights safely. | Admin | Allowed users table | Switches PATCH isActive/isAdmin; current admin cannot disable own active/admin; admin grant updates profile and room memberships; messages show success/errors. | src/components/admin/AllowedUsersManager.tsx; src/app/api/admin/allowed-users/route.ts | Implemented | Component Covered | tests/components/admin-controls.test.tsx | Toggle another user and attempt self-disable; verify route responses. |  | No Defect | Passed
F065 | Admin | Room membership management | As an admin, I want to grant or remove room roles for existing and invited users across multiple rooms. | Admin | Membership manager | Combines profiles and active allowed users without profiles as pending targets; supports role selection, all/clear room selection, multi-room update/remove, pending memberships, and audit per room. | src/components/admin/MembershipManager.tsx; src/app/api/admin/memberships/route.ts | Implemented | Component Covered | tests/components/admin-controls.test.tsx | Grant/remove member/admin/observer for profile and pending email targets. |  | No Defect | Passed
F066 | Admin/Ops | Operations dashboard | As an operator, I want agent-run, failure, memory-review, and audit summaries so I can inspect risks. | Admin/operator | /admin/ops | Shows metrics for agent runs, failed runs, requires_action runs, pending memory reviews, Google Meet connect CTA, recent agent_runs, and recent audit_logs. | src/components/admin/OpsDashboard.tsx; src/app/(workspace)/admin/ops/page.tsx | Implemented | Browser Smoke Covered | post-fix browser/admin render retest | Open ops with seeded runs/logs/reviews; verify metrics and lists. |  | No Defect | Passed for render
F067 | Briefings | Coordinator briefing snapshot and generation | As a meeting member, I want a structured cross-room briefing so the main meeting can see room highlights, risks, decisions needed, and next actions. | Meeting member | GET/POST /api/coordinator/briefing | GET returns latest coordinator briefing and recent room briefings; POST creates ready room briefings for active non-meeting rooms, then a coordinator briefing with cross-room risks/decisions/actions, and logs audit. | src/app/api/coordinator/briefing/route.ts; src/server/coordinator/coordinator-briefing-service.ts | Implemented | Unit Covered | tests/unit/coordinator-briefing.test.ts | Generate briefing with active tasks, pending imports, and overdue tasks; verify counts and audit. |  | No Defect | Passed
F068 | Agents/Tools | Managed-agent custom tool registry | As a domain bot, I need safe backend tools instead of direct DB access. | Agent | Claude Managed Agents tool config | Tool registry exposes read/search/list/share/task/memory-review capabilities as custom tools, flags risk/writes, and keeps memory writes behind review tooling. | src/server/agents/tools/tool-registry.ts; src/server/agents/tools/execute-tool.ts; docs/AGENT_TOOLS.md | Implemented | Unit Covered | tests/unit/tool-registry.test.ts | Inspect tool configs and execute read/write tools through wrapper with permission checks. |  | No Defect | Passed
F069 | Agents/Memory | Domain memory and Claude memory attachments | As a bot, I want room memory and pending context to shape responses without leaking data across rooms. | Agent | Agent startup context | Memory service returns startup context, project observer context, read-only Claude memory resources, pending context append/process/update functions, and local domain_memory cache updates. | src/server/memory/domain-memory-service.ts; src/server/agents/claude-managed-agent-adapter.ts | Implemented | Unit Covered | tests/unit/domain-memory.test.ts; tests/unit/thread-context.test.ts | Run memory attachment and pending context flow for a room and global development observer. |  | No Defect | Passed
F070 | Security/Data | Tenant-isolated list APIs | As a user, I should not list shared items, meeting imports, files, tasks, or rooms outside my membership. | Room member | List APIs | List routes require auth and membership filters; no-room list endpoints filter by user's room IDs; room-specific queries require room membership. | src/server/auth/require-room-member.ts; src/app/api/shared-items/route.ts; src/app/api/meeting-imports/route.ts; src/app/api/tasks/route.ts; src/app/api/files/route.ts | Implemented | Unit Covered | tests/unit/list-route-authorization.test.ts | Run list routes with user who has meeting only and with work-room membership. |  | No Defect | Passed
F071 | Security/Data | Audit logging for major writes | As an operator, I want major write operations recorded so sensitive student or organizational data changes are traceable. | Operator | Write services/routes | Thread create/update, decisions, tasks, user/admin changes, video meetings, coordinator briefings, file/share/import actions, and profile updates write audit logs through store. | src/server/audit/audit-service.ts; src/server/data/mock-store.ts; src/server/data/supabase-store.ts | Implemented | Representative Unit Covered | tests/unit/file-upload-limits.test.ts; tests/unit/video-meeting-service.test.ts; existing write-flow tests | Exercise representative write flows and verify audit_logs entries. |  | No Defect | Representative audit paths passed
F072 | System/API | JSON error response normalization | As a client, I want API failures to return consistent status and message payloads. | Client/UI | All API routes through jsonError | Known HttpError/AuthError/ForbiddenError map to intended status; generic errors become JSON error response without crashing callers. | src/lib/api.ts; src/lib/http-error.ts; src/server/auth/errors.ts | Implemented | Unit Covered | tests/unit/json-error.test.ts | Throw known and unknown errors through route handler and verify response shape. |  | No Defect | Passed

## Test Log
Story ID | Test Type | Command or Steps | Result | Evidence | Errors Found | Tested At | Retest Result
ALL | Automated | pnpm lint | Passed | ESLint completed without errors. |  | 2026-06-24 15:40 KST | Passed
ALL | Automated | pnpm typecheck | Passed | tsc --noEmit completed without errors. |  | 2026-06-24 15:40 KST | Passed
ALL | Automated | pnpm test | Passed | Vitest: 34 files passed, 155 tests passed. |  | 2026-06-24 15:40 KST | Passed
ALL | Browser/E2E | pnpm test:e2e --workers=1 --reporter=list | Passed | Playwright smoke: 8 passed across chromium and mobile. | Original smoke setup was out of sync with mock mode; tracked as D007 and fixed. | 2026-06-24 15:40 KST | Passed
ALL | Build | pnpm build | Passed | Next build compiled successfully and generated 34 app pages. |  | 2026-06-24 15:40 KST | Passed
UI-FIX | Browser | Manual Playwright script against http://127.0.0.1:3137 for office, admin sidebar, meeting task dialog, video start dialog, and finance chat send. | Passed | Office/admin/meeting fixed flows passed; video default title rendered 6월 24일 회의; chat message displayed. |  | 2026-06-24 15:17 KST | Passed
TEST-INFRA | Automated | Initial pnpm test:e2e and incorrect pnpm argument run | Fixed | Config now starts Next in mock mode; smoke spec now matches mock redirect and exact heading. | D007 | 2026-06-24 15:17 KST | Passed
COVERAGE-BATCH-2 | Automated | pnpm exec vitest run tests/unit/auth-routes.test.ts tests/components/top-header.test.tsx tests/components/cards.test.tsx tests/components/room-interactions.test.tsx tests/components/message-bubble.test.tsx tests/components/admin-controls.test.tsx tests/unit/file-upload-limits.test.ts tests/unit/video-meeting-service.test.ts | Passed | Focused coverage batch: 8 files passed, 46 tests passed. |  | 2026-06-24 15:30 KST | Passed
DORMANT-FIX | Automated | pnpm exec vitest run tests/components/video-meeting.test.tsx; rg FileShareToMeetingButton -n src tests | Passed | Video meeting dormant-action regression passed: 1 file, 4 tests; obsolete FileShareToMeetingButton has no remaining references. |  | 2026-06-24 15:37 KST | Passed

## Defects
Defect ID | Story IDs | Priority | Category | Title | Observed | Expected | Status | Code References | Source | Retest Status | Fix Notes
D001 | F052 | P3 | UX | Video meeting default title is stale | Start dialog defaults to '5월 정기 회의' even though the current audit date is 2026-06-24. | Default meeting title should not be tied to a stale month; it should be neutral or date-derived. | Fixed | src/components/video-meetings/VideoMeetingStartDialog.tsx | Code review | Passed | Default meeting title is generated from the current Asia/Seoul date; component and browser retests passed.
D002 | F008 | P2 | UX | Sidebar always marks meeting link active | SidebarPanel receives no current route and passes active to the meeting link unconditionally. | Only the current room/link should show active styling. | Fixed | src/components/layout/SidebarPanel.tsx; src/components/layout/AppShell.tsx | Code review | Passed | AppShell passes activeRoomId and SidebarPanel only highlights the explicit active room; component and browser retests passed.
D003 | F049,F050 | P3 | UX | Research-association room names get an extra 방 suffix in task UI | DecisionTaskPanel displayRoomName handles names ending in 방 or 실 but not 연구회, so project rooms such as 경기도교육연구회 can render as 경기도교육연구회방. | Names ending in 연구회 should be displayed as-is, consistent with file sharing UI. | Fixed | src/components/rooms/DecisionTaskPanel.tsx | Code review | Passed | Task room-name formatter now leaves names ending in 연구회 unchanged; browser retest passed.
D004 | F040 | P3 | UX | Shared-item import dialog may add 방 suffix to research-association rooms | SharedItemCard displayRoomName handles 방 and 실 only, while FileList handles 연구회 too. | Meeting import target labels should display research-association names as-is. | Fixed | src/components/meeting/SharedItemCard.tsx | Code review | Passed | Shared-item import room-name formatter now leaves names ending in 연구회 unchanged; component coverage added.
D005 | F044 | P4 | Logistical | Single-file share-to-meeting component is dormant | FileShareToMeetingButton implements an older one-file meeting share flow but is not referenced by mounted FileList. | Dormant code should be removed, mounted intentionally, or tracked as future UI to avoid misleading maintenance. | Fixed | src/components/files/FileShareToMeetingButton.tsx; src/components/files/FileList.tsx | Code review | Passed | Removed obsolete unmounted FileShareToMeetingButton; active FileList multi-room sharing remains covered.
D006 | F058,F061 | P3 | UX | Meeting artifact/summary action buttons are inert if mounted | VideoMeetingArtifactCard and CreateDecisionTaskFromSummary render buttons without handlers, and related components are not mounted. | Buttons should either perform actions, be disabled with unavailable state, or remain unmounted until implemented. | Fixed | src/components/video-meetings/VideoMeetingArtifactCard.tsx; src/components/video-meetings/CreateDecisionTaskFromSummary.tsx | Code review | Passed | Dormant artifact/summary conversion buttons now render disabled until handlers are implemented; component regression coverage added.
D007 | TEST-E2E | P3 | Test Infrastructure | Playwright smoke suite was out of sync with mock mode | Mock-mode e2e expected the login page to render even though mock auth redirects authenticated users to /office; meeting heading selector also matched multiple headings. | Smoke suite should run deterministically in mock mode on desktop and mobile projects. | Fixed | playwright.config.ts; tests/e2e/smoke.spec.ts | Automated e2e retest | Passed | Web server command now enables NEXT_PUBLIC_USE_MOCK_DATA; root/login smoke asserts mock redirect; meeting heading assertion uses exact matching. Retest passed: 8 Playwright checks.

## Dormant Backlog
ID | Item | Code Reference | Current State | Recommended Handling
B002 | MeetingSummaryReview | src/components/video-meetings/MeetingSummaryReview.tsx | Presentational card only and not mounted. | Mount in a meeting artifacts workflow or remove until needed.
B003 | CreateDecisionTaskFromSummary | src/components/video-meetings/CreateDecisionTaskFromSummary.tsx | Not mounted; conversion buttons are disabled until decision/task/import handlers are wired. | Wire to decisions/tasks/import APIs before enabling these controls.
B004 | VideoMeetingArtifactCard | src/components/video-meetings/VideoMeetingArtifactCard.tsx | Not mounted; artifact conversion buttons render disabled until handlers are wired. | Add handlers when meeting artifact review UI is built, then enable the controls.
B005 | ZoomMeetingEmbed | src/components/video-meetings/ZoomMeetingEmbed.tsx | Placeholder card, not mounted. | Only mount after Meeting SDK flow is implemented and gated.
B006 | ZoomFallbackCard | src/components/video-meetings/ZoomFallbackCard.tsx | Fallback card, not mounted. | Use with Zoom embed when enabled.

## Route API Matrix
Route or Surface | Method | Primary Feature IDs | Auth Gate | Expected Result
/ | GET | F001 | Current user optional | Redirects to /office or /login.
/login | GET | F002 | Redirects authenticated user | Shows login actions and error messaging.
/auth/login | GET | F003 | Mock bypass or Supabase OAuth | Starts Google OAuth or redirects to office in mock mode.
/auth/callback | GET | F003 | OAuth callback | Onboards approved user or redirects with error.
/auth/dev-login | GET | F004 | Host/env enabled | Sets app session for configured dev user.
/logout | GET | F005 | No hard auth requirement | Clears session and redirects to login.
/office | GET | F010,F011,F012 | requireUser | Renders office map and side panel.
/rooms/{roomId} | GET | F013-F050,F060 | requireUser + requireRoomMember | Renders room workspace for active room.
/admin | GET | F062-F065 | requireAdmin | Renders admin dashboard.
/admin/ops | GET | F066 | requireAdmin | Renders operations dashboard.
/api/rooms/{roomId}/messages | GET/POST | F019,F020 | requireUser + room membership/write via service | Lists or creates room messages.
/api/rooms/{roomId}/threads | GET/POST | F015,F016 | requireUser + room membership | Lists or creates room threads.
/api/rooms/{roomId}/threads/{threadId} | PATCH | F017 | requireUser + room membership | Updates thread metadata.
/api/rooms/{roomId}/agent-runs | POST | F021-F024 | requireUser + service checks | Starts agent run and schedules completion.
/api/rooms/{roomId}/agent-runs/{runId} | GET/DELETE | F024 | requireUser + run access | Reads or cancels agent run.
/api/files | GET/POST/DELETE | F031-F033 | requireUser + file/room service checks | Lists, uploads, or removes room file access.
/api/files/{id}/download | GET | F032 | requireUser + file access | Returns signed download URL.
/api/files/{id}/versions | POST | F034 | requireUser + file access | Creates file version.
/api/files/share-targets | GET | F035 | requireUser + membership filtering | Returns writable target rooms.
/api/files/share | POST | F036 | requireUser + source/target checks | Shares selected files to target rooms.
/api/shared-items | GET/POST | F037,F044 | requireUser + service checks | Lists or creates shared items.
/api/shared-items/{id} | DELETE | F039 | requireUser + service checks | Deletes shared item record.
/api/shared-items/{id}/open-original | GET/POST | F038 | requireUser + service checks | Returns default dir or downloads/opens original.
/api/meeting-imports | GET/POST | F040 | requireUser + service checks | Lists or creates meeting imports.
/api/meeting-imports/targets | GET | F040 | requireUser + writable-room filtering | Lists import target rooms.
/api/meeting-imports/{id}/apply | POST | F041 | requireUser + import access | Applies import to bot memory.
/api/meeting-imports/{id}/task | POST | F042 | requireUser + import access | Creates task from import.
/api/meeting-imports/{id} | DELETE | F043 | requireUser + import access | Deletes import record.
/api/decisions | GET/POST | F045,F046 | requireUser + meeting membership/write | Lists or creates meeting decisions.
/api/decisions/{id} | PATCH/DELETE | F047 | requireUser + meeting write | Updates or deletes decision.
/api/tasks | GET/POST | F048-F050 | requireUser + room/write checks | Lists or creates tasks.
/api/video-meetings | GET/POST | F051,F052 | requireUser + service checks | Lists or creates/reuses meetings.
/api/video-meetings/{id} | GET | F058-F060 | requireUser + room membership | Reads meeting and artifacts without hostUrl.
/api/video-meetings/{id}/join-url | PATCH | F053 | requireUser + meeting access | Registers normalized join URL.
/api/video-meetings/{id}/join | POST | F054 | requireUser + meeting access | Records join intent.
/api/video-meetings/{id}/end | POST | F055 | requireUser + meeting access | Ends meeting.
/api/video-meetings/{id}/artifacts | POST | F058 | requireUser + meeting access | Creates artifact.
/api/video-meetings/{id}/summarize | POST | F059 | requireUser + meeting access | Creates summary artifact.
/api/video-meetings/zoom/signature | POST | F057 | requireUser + Zoom meeting access | Returns participant signature or setupRequired.
/api/admin/allowed-users | GET/POST/PATCH | F063,F064 | requireAdmin | Lists, invites, or updates allowed users.
/api/admin/memberships | GET/POST | F065 | requireAdmin | Lists or mutates room memberships.
/api/profile | PATCH | F007 | requireUser | Updates profile and audits changes.
/api/coordinator/briefing | GET/POST | F067 | requireUser + meeting membership | Gets or generates coordinator briefing.
/api/office/operation-status | GET | F011,F077 | requireUser | Returns status counts.
/api/agent-runs/sweep | GET/POST | F030 | CRON_SECRET bearer | Sweeps stuck agent runs.
/api/health | GET | F009 | Public | Returns safe health status.
/api/auth/debug | GET | F006 | Debug enabled | Returns safe auth diagnostics or 404.